## Sheet1
| Friday |  |  |  | Saturday
| 2300 | 0000 | 0100 | <====> | 0900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000 | 2100 | 2200 | 2300 | 0000
Ideas Creation (GHS+SW)
Design Spec (GHS)
Tech Spec (GHS)
Initial Spritework (SW) | [6 empty] | Dependency on Design Spec, Expected 4-6hrs work to be fit in this time slot. | [13 empty] | Flexitime
Sound Design (GHS) | [7 empty] | Expected 4-6hrs work, to be fit around prototyping. Assets to most likely be created on an as-needed basis
Prototyping(GHS) | [7 empty] | Dependency on Design/Tech Spec
| Saturday |  |  | Sunday
| 0000 | 0100 | <====> | 0900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000 | 2100 | 2200 | 2300 | 0000
Initial Spritework (SW) |  |  |  | Dependency on Design Spec, Expected 4-6hrs work to be fit in this time slot.
Sound Design (GHS) |  |  |  | Expected 4-6hrs work, to be fit around prototyping
Prototyping(GHS) |  |  |  | Dependency on Design/Tech Spec
QA(All) | [13 empty] | Dependency on Prototyping
| Sunday |  |  | Sunday
| 0000 | 0100 | <====> | 0900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000 | 2100 | 2200 | 2300
QA(All) | [6 empty] | Simultaneous | [10 empty] | END
Amends(All) | [6 empty] | Simultaneous